PART III

Task Breakdown

& Implementation Roadmap

Strategic-to-Operational Human-Supervised Supply Chain Twin

4-Week Sprint Plan with Deliverables, Decision Points & Checklists

Tianshi Wang

emlyon business school — March 2026

Implementation Overview

Critical Path

The project has a clear critical path—four tasks that every other task depends on. If you fall behind on anything, protect these four:

Twin State Schema (Task 1.1) → Synthetic Cases (Task 1.3) → Governance Agent (Task 2.4) → Streamlit UI (Task 3.1)

Everything else connects to these four. The twin state schema defines the data contract for all agents. The synthetic cases provide ground truth for evaluation. The Governance Agent is the thesis’s core contribution made tangible. The Streamlit UI is what the audience sees during the demo.

4-Week Overview

| Week | Theme | Core Deliverables | End-of-Week Milestone |
| --- | --- | --- | --- |
| 1 | Foundation | Twin state schema, scenario configs, synthetic cases, RAG knowledge base | Can load a scenario, inject shock, and compute cost manually |
| 2 | Agents & Workflow | LangGraph graph, 3 agents, supervisor node, weather API | Can run full pipeline in notebook: scenario → agents → recommendation |
| 3 | UI & Evaluation | Streamlit app, evaluation engine, integration testing | Complete interactive demo running end-to-end |
| 4 | Polish & Present | Demo rehearsal, slides, report, code cleanup | Submission-ready package + rehearsed presentation |

Week 1: Foundation

Goal: Build the data layer that everything else depends on. By end of week, you should be able to load a scenario, inject a disruption, compute costs, and query the RAG knowledge base—all without any LLM calls.

Task 1.1: Design Twin State Schema

CRITICAL PATH This is the single most important design decision. Every agent prompt, every evaluation metric, and every UI element depends on this schema.

Description

Define the Python data structure for the supply chain twin state. Use Pydantic models for type safety and validation. The state must be a proper data object with methods, not a JSON blob.

Deliverable

File: src/twin_state.py

Contains the following classes and methods:

- Supplier: id, name, lead_time_days, reliability_score (0–1), capacity_units, is_active

- Warehouse: id, name, location (lat/lon), max_capacity, current_inventory, operating_cost_per_unit

- Carrier: id, name, available (bool), cost_per_unit, transit_time_hours, capacity_limit

- CustomerZone: id, name, demand_units, sla_deadline_hours, sla_penalty_per_hour

- TwinState: suppliers[], warehouses[], carriers[], customer_zones[], current_disruptions[], timestamp

- Methods: initialize_from_config(path), inject_shock(shock_config), apply_action(action), compute_total_cost(), to_prompt_context() (serializes state for LLM consumption)

Decisions Needed

| Decision | Options | Recommendation |
| --- | --- | --- |
| Cost function type | Linear / piecewise / stochastic | Linear for MVP. Simple, transparent, debuggable. |
| SLA penalty structure | Fixed per violation / per hour late / tiered | Per-hour linear penalty. Easy to compute, creates meaningful cost differences. |
| Expediting cost model | Fixed surcharge / multiplier on base cost | 2x multiplier on base carrier cost. Simple and intuitive. |
| Transfer cost model | Fixed + per-unit / distance-based | Fixed fee + per-unit cost. Two parameters, sufficient for MVP. |

Acceptance Criteria

- TwinState can be initialized from a JSON config file

- inject_shock() modifies the correct state variables

- apply_action() updates inventory, carrier status, and costs correctly

- compute_total_cost() returns a deterministic numeric result

- to_prompt_context() produces a clean string representation for LLM consumption

- All classes have type hints and Pydantic validation

Task 1.2: Create Scenario Configs

Description

Design 5–8 disruption scenarios as JSON files. Each scenario represents a specific disruption event that modifies the baseline twin state. Scenarios should vary in severity, type, and which entities are affected.

Deliverable

Folder: data/scenarios/ with 5–8 JSON files

Scenario Set Design

| # | Scenario Name | Disruption Type | Severity |
| --- | --- | --- | --- |
| 1 | Winter Storm — Chicago Hub | Weather: Carrier A unavailable, transit +24h | High |
| 2 | Supplier Shutdown — Shenzhen | Supplier failure: Supplier A inactive | High |
| 3 | Holiday Demand Surge | Demand: Zone A demand +80% | Medium |
| 4 | Port Congestion — LA | Logistics: All carrier transit +36h | High |
| 5 | Warehouse Equipment Failure | Capacity: WH-A capacity -50% | Medium |
| 6 | Minor Delay — Routine | Carrier B transit +8h | Low |
| 7 | Compound: Storm + Demand | Weather + demand surge combined | Critical |

JSON Structure per Scenario

Each scenario config should include: scenario_id, name, description, severity (low/medium/high/critical), disruption_type, affected_entities (list of entity IDs and which fields change), weather_location (lat/lon for API call), weather_fallback (pre-written weather context if API fails), and difficulty_notes (for your own reference during case design).

Acceptance Criteria

- Each scenario can be loaded by TwinState.initialize_from_config()

- At least 3 disruption types represented (weather, supplier, demand)

- At least 1 compound scenario (multiple simultaneous disruptions)

- Severity distribution: 1–2 low, 2–3 medium, 2 high, 1 critical

Task 1.3: Prepare Synthetic Cases with Ground Truth

CRITICAL PATH Without ground truth labels, you cannot compute unnecessary override rate, override effectiveness, or regret. These are the metrics that make the project’s evaluation framework meaningful.

Description

Create 10–15 exception cases, each representing a specific fulfillment problem within a disruption scenario. Each case must be pre-computed with a cost-optimal action so that evaluation metrics can be calculated.

Deliverable

Folder: data/cases/ with 10–15 JSON files

File: data/case_summary.csv (overview table of all cases with their optimal actions and costs)

Case Structure

Each case JSON includes:

- case_id, scenario_id (which scenario it belongs to)

- exception_description (natural language: what went wrong)

- initial_state_snapshot (twin state at the moment of the exception)

- available_actions: list of 3–4 possible actions, each with action_id, action_type, description

- cost_per_action: for each action, the computed total_cost (direct + downstream)

- optimal_action: the action_id with the lowest total cost

- optimal_cost: the total cost of the optimal action

- agent_recommendation: what the agent should recommend (usually = optimal, but in 2–3 cases deliberately non-optimal to test override detection)

- difficulty: easy / medium / hard

Difficulty Distribution

- Easy (4 cases): The optimal action is obviously best. Large cost gap between optimal and alternatives. Tests whether the human trusts the agent when it’s clearly right.

- Medium (5 cases): The optimal action is better but not dramatically so. Cost gaps are modest. Tests human judgment under ambiguity.

- Hard (3–4 cases): Costs are close. The optimal action may be counterintuitive. In 2–3 of these cases, the agent deliberately recommends a suboptimal action to test whether the human catches the error.

Acceptance Criteria

- 10–15 cases with complete cost calculations

- Each case has exactly one optimal action determined by minimum total cost

- 2–3 cases where agent recommendation is deliberately suboptimal

- Difficulty distribution: ~4 easy, ~5 medium, ~4 hard

- cost_per_action values are internally consistent with the cost function

Task 1.4: Build RAG Knowledge Base

Description

Write 3–5 markdown documents representing operational knowledge. Chunk, embed, and store in a FAISS vector database. Build a retrieval function that agents can call.

Deliverable

Folder: data/knowledge/ with 3–5 markdown files

File: src/rag_setup.py (builds vector store, provides retrieve(query, k) function)

Knowledge Documents

| Document | Content | Used By |
| --- | --- | --- |
| exception_handling_sop.md | Step-by-step procedures for common exceptions: shipment delay, stockout, demand surge, supplier failure | Operations Agent, Governance Agent |
| sla_terms.md | SLA definitions, penalty rates, escalation thresholds, customer tier classifications | Cost Agent, Governance Agent |
| carrier_selection_rules.md | Carrier selection criteria, cost tables, expediting rules, backup carrier protocols | Operations Agent |
| escalation_protocol.md | When to escalate to human, override guidelines, post-override review requirements | Governance Agent |
| inventory_transfer_policy.md | Cross-warehouse transfer rules, minimum quantities, lead times, cost allocation | Operations Agent, Cost Agent |

Technical Setup

- Chunking: RecursiveCharacterTextSplitter, chunk_size=400, overlap=80

- Embedding: OpenAI text-embedding-3-small (or sentence-transformers/all-MiniLM-L6-v2 for cost savings)

- Vector store: FAISS (local, no server, fast for small corpus)

- Retrieval function: retrieve(query: str, k: int = 4) → list of (chunk_text, source_doc, similarity_score)

Acceptance Criteria

- Vector store builds without errors from the markdown documents

- retrieve() returns relevant chunks for test queries (e.g., “shipment delay SOP” returns chunks from exception_handling_sop.md)

- Retrieval latency < 500ms for the small corpus

Week 2: Agents & Workflow

Goal: Build the complete LangGraph pipeline. By end of week, you should be able to run the full agent chain in a Jupyter notebook: load scenario → inject disruption → Operations + Cost agents analyze → Governance Agent synthesizes recommendation → print output.

Task 2.1: Set Up LangGraph Graph Structure

Description

Define the StateGraph with all nodes, edges, and the state schema. This is the orchestration backbone.

Deliverable

File: src/graph.py

Contains:

- GraphState TypedDict or Pydantic model with all state fields

- Node function stubs for all 7 nodes (can return placeholder outputs initially)

- Edge definitions including fan-out (Operations + Cost parallel) and conditional routing (supervisor decision)

- Graph compilation and a test invocation with dummy data

Acceptance Criteria

- Graph compiles without errors

- Graph visualization (graph.get_graph().print_ascii()) shows correct structure

- Can invoke graph with dummy state and see it flow through all nodes

Task 2.2: Implement Operations Agent

Description

The Operations Agent receives twin state + disruption context, queries RAG for relevant SOPs, and outputs ranked action recommendations with feasibility assessments.

Deliverable

File: src/agents/operations_agent.py

Key components:

- System prompt defining the agent’s role, expertise domain, and output format

- RAG integration: queries the knowledge base for relevant SOP passages

- Structured output: returns JSON with ranked_actions (list of action objects with action_id, description, feasibility_score, rationale)

- Input: twin state (via to_prompt_context()) + disruption description + retrieved SOP chunks

Decisions Needed

- LLM choice: GPT-4o is recommended for reliable structured output (function calling / JSON mode). Claude Sonnet is an alternative. For cost savings during development, GPT-4o-mini can be used for iteration and switched to GPT-4o for final demo.

Acceptance Criteria

- Agent returns valid structured JSON output for 3 different scenario inputs

- RAG retrieval is integrated and cited in agent’s rationale

- Actions recommended are from the predefined action set (no hallucinated actions)

Task 2.3: Implement Cost Agent

Description

The Cost Agent estimates costs for each proposed action. It can be partially rule-based: use the twin state’s cost parameters for deterministic calculation, and use the LLM only for downstream recovery cost estimation.

Deliverable

File: src/agents/cost_agent.py

Key components:

- Deterministic cost calculation function using twin state parameters (direct costs)

- LLM-assisted estimation for downstream recovery costs (SLA penalties, backlog effects)

- Structured output: returns JSON with cost_estimates (list per action: action_id, direct_cost, recovery_cost, total_cost, cost_breakdown_explanation)

Design insight: Making the Cost Agent partially rule-based actually strengthens the project. It demonstrates that not every agent needs to be a pure LLM call—some are better served by deterministic computation with LLM-generated explanations. This shows architectural sophistication.

Acceptance Criteria

- Cost estimates are consistent with twin state parameters

- Direct costs are deterministic (same input = same output)

- Output includes human-readable cost breakdown explanation

Task 2.4: Implement Governance Agent

CRITICAL PATH This is the thesis’s core contribution made tangible. The Governance Agent embodies both uncertainty expression and traceability-oriented governance. Spend extra time on the output format design.

Description

The Governance Agent receives outputs from Operations and Cost agents, synthesizes them into a unified recommendation with structured uncertainty expression and rationale trace.

Deliverable

File: src/agents/governance_agent.py

Output Format (Critical Design)

The Governance Agent must produce a structured output with exactly these fields:

| Field | Description | Thesis Concept |
| --- | --- | --- |
| risk_level | LOW / MEDIUM / HIGH — overall risk assessment for this exception | Uncertainty Expression |
| situational_explanation | 2–3 sentence explanation of why this risk level was assigned | Uncertainty Expression |
| recommended_action | The selected action from the action set, with a brief justification | Decision Output |
| evidence_sources | List of SOPs, rules, and data points that drove the recommendation | Traceability Governance |
| cost_summary | Key cost figures from the Cost Agent, summarized for the supervisor | Traceability Governance |
| confidence_note | Any caveats, assumptions, or areas of uncertainty in the recommendation | Uncertainty Expression |
| rationale_trace | Step-by-step reasoning: how inputs were weighed, which trade-offs were made | Traceability Governance |
| alternative_actions | Other considered actions with brief reasons for not selecting them | Traceability Governance |

Acceptance Criteria

- Output contains ALL 8 structured fields

- risk_level is always one of LOW / MEDIUM / HIGH (validated)

- evidence_sources references specific SOP documents and cost data

- rationale_trace shows clear reasoning steps, not generic text

- Output is parseable as JSON for downstream UI rendering

Task 2.5: Implement Supervisor Node

Description

Build the human checkpoint node using LangGraph’s interrupt mechanism.

Deliverable

File: src/supervisor.py

Three decision paths:

- Approve: Accept recommendation → apply recommended action to twin state

- Verify: Request additional info → trigger extra RAG retrieval or cost detail → return to decision

- Override: Select alternative action from action set → apply override action to twin state → record as override event

Acceptance Criteria

- Graph correctly pauses at supervisor node and waits for input

- All three decision paths produce correct state updates

- Override events are recorded with timestamp and rationale for evaluation

Task 2.6: Integrate Weather API

Description

Connect Open-Meteo API. Build fetch function with fallback.

Deliverable

File: src/external/weather.py

- fetch_weather(lat, lon) → dict with temperature, precipitation, wind_speed, weather_description

- Fallback: if API call fails (timeout, network error), return scenario’s weather_fallback data

- Weather data is injected into disruption context string for LLM consumption

Acceptance Criteria

- API call succeeds for at least 2 different coordinates

- Fallback activates gracefully on network failure (test by disconnecting)

- Weather data is formatted as human-readable context string

Week 3: UI, Evaluation & Integration

Goal: Build the Streamlit UI and evaluation engine. By end of week, you should have a fully functional interactive demo that can run any case from scenario selection to cost comparison.

Task 3.1: Build Streamlit Interface

CRITICAL PATH This is what the audience sees. A clean, functional UI with clear information hierarchy is more persuasive than sophisticated backend logic that is invisible.

Description

Create the interactive web application that wraps the LangGraph pipeline.

Deliverable

File: app.py (~250–350 lines)

UI Layout Specification

Sidebar:

  - Scenario dropdown selector (shows scenario name + severity badge)

  - Twin State summary cards: total inventory, active carriers, active suppliers, current disruptions

  - Run Analysis button

Main Area — Analysis Phase:

  - Two columns: Operations Agent output (left) and Cost Agent output (right)

  - Each column shows the agent’s key findings in a card-style layout

Main Area — Governance Recommendation:

  - Risk level badge (colored: green/yellow/red)

  - Situational explanation (prominent text)

  - Recommended action (highlighted card)

  - Expandable sections: rationale trace, evidence sources, alternative actions, cost summary

Main Area — Supervisor Decision:

  - Three buttons: Approve / Verify / Override

  - If Override: dropdown to select alternative action from action set

  - Confirmation step before applying decision

Main Area — Results:

  - Cost comparison: agent recommendation cost vs. actual decision cost

  - Verdict: “Necessary override” / “Unnecessary override” / “Approved (correct)” / “Approved (missed intervention)”

  - Updated twin state summary

Acceptance Criteria

- All UI sections render correctly for all scenario types

- Session state persists correctly across button clicks

- Expandable sections work for rationale trace

- Risk level badge displays correct color

- Override flow correctly shows action dropdown and applies selected action

Task 3.2: Implement Evaluation Engine

Description

Build the evaluation logic that computes all supervision calibration metrics.

Deliverable

File: src/evaluation.py

Functions

| Function | Inputs | Returns |
| --- | --- | --- |
| compute_total_cost(state, action) | Twin state + chosen action | Float: total cost (direct + downstream) |
| is_unnecessary_override(case, human_action) | Case ground truth + human’s chosen action | Bool: True if agent was optimal and human overrode |
| compute_override_effectiveness(case, human_action) | Case ground truth + human’s chosen action | String: “cost_reducing” / “cost_increasing” / “neutral” |
| compute_regret(case, human_action) | Case ground truth + human’s chosen action | Float: actual_cost - optimal_cost |
| aggregate_metrics(all_case_results) | List of per-case results | Dict: aggregate metrics across all cases |

Acceptance Criteria

- compute_total_cost matches pre-computed ground truth values

- is_unnecessary_override correctly identifies overrides of optimal actions

- aggregate_metrics produces a summary dict suitable for dashboard display

Task 3.3: End-to-End Integration Testing

Description

Run all 10–15 cases through the complete pipeline. Fix edge cases. Verify consistency.

Deliverable

File: tests/integration_test.py (or a test notebook)

Test Checklist

- All scenarios load without errors

- All agents produce valid structured output for all cases

- Governance Agent risk_level is always one of LOW / MEDIUM / HIGH

- Cost calculations are consistent (same case, same action = same cost)

- UI renders correctly for low, medium, and high severity scenarios

- Override flow works end-to-end

- Weather API fallback activates correctly when API is unavailable

- Evaluation metrics match expected values for 3+ manually verified cases

Week 4: Polish & Present

Goal: Prepare everything for submission and presentation. By end of week, you should have a submission-ready package and a rehearsed, timed presentation.

Task 4.1: Demo Rehearsal

Description

Rehearse the demo at least 3 times. Time each section. Prepare contingency for failures.

Deliverable

Output: Rehearsed demo with timing notes

Demo Script (15 minutes)

| Time | Section | Content | Show |
| --- | --- | --- | --- |
| 0–2 min | Context | Business problem, calibrated supervision concept | 1–2 slides |
| 2–3 min | Architecture | Three-layer diagram, agent roles, LangGraph workflow | Architecture slide |
| 3–4 min | Scenario | Select “Winter Storm — Chicago Hub”, show twin state | Live demo: sidebar |
| 4–7 min | Agent Analysis | Show Operations + Cost agent outputs side by side | Live demo: main area |
| 7–10 min | Governance | Show recommendation with risk label, rationale trace, evidence | Live demo: governance card |
| 10–12 min | Decision | Approve case, then override case; show cost comparison | Live demo: buttons + results |
| 12–14 min | Evaluation | Show aggregate metrics across cases; connect to thesis insight | Live demo or slide |
| 14–15 min | Wrap-up | Contributions, limitations, future work | 1 slide |

Contingency Plan

- If LLM API is slow: Pre-cache at least 2 complete case runs. Show the cached results with explanation.

- If Weather API fails: Fallback activates automatically. Mention it as a design feature.

- If Streamlit crashes: Have a backup notebook with the same case pre-run. Switch to notebook demo.

Task 4.2: Prepare Presentation Slides

Deliverable

File: Slide deck (15–20 slides, PPT or Google Slides)

Suggested Slide Structure

- Title slide

- Business problem: fulfillment exceptions + coordination gap

- Why it matters: digital twins + GenAI + human-AI teaming

- Theoretical foundation: calibrated supervision (1 slide, brief)

- Course requirement mapping table

- System architecture: three-layer diagram

- LangGraph workflow: 7-node graph visualization

- Agent roles: 3+1 structure with responsibilities

- RAG design: two-layer knowledge architecture

- LIVE DEMO (slides pause here — switch to Streamlit)

- Evaluation metrics and results

- Key insight: unnecessary overrides increase cost

- Innovation and contributions

- Limitations and future work

- Q&A

Presentation tip: Spend at most 4 minutes on slides 1–9 (theory + architecture). Spend at least 8 minutes on the live demo (slides 10–12). The demo IS the argument. Evaluators remember what they saw working, not what they read on slides.

Task 4.3: Write Project Report

Deliverable

File: Final report document covering all 4 course requirement steps

Suggested structure: Introduction and business problem, model selection and justification, model adaptation (RAG + prompt engineering), implementation (system architecture, LangGraph workflow, agent design, UI), evaluation results and analysis, theoretical contributions and practical implications, limitations and future work, references.

Task 4.4: Code Cleanup & Repository

Deliverable

Output: Clean GitHub repository

Repository Structure

supply-chain-twin/

- README.md (setup instructions, demo instructions, architecture overview)

- requirements.txt (all Python dependencies with versions)

- .env.example (template for API keys)

- app.py (Streamlit entry point)

- src/ (graph.py, twin_state.py, evaluation.py, supervisor.py)

- src/agents/ (operations_agent.py, cost_agent.py, governance_agent.py)

- src/external/ (weather.py)

- data/scenarios/ (JSON scenario configs)

- data/cases/ (JSON case files with ground truth)

- data/knowledge/ (markdown SOP documents)

- tests/ (integration tests)

Acceptance Criteria

- Repository can be cloned and run with: pip install -r requirements.txt && streamlit run app.py

- README includes clear setup instructions and architecture diagram

- .env.example lists all required environment variables

- No hardcoded API keys in code

Dependency Map & Risk Register

Task Dependencies

| Task | Depends On | Blocks |
| --- | --- | --- |
| 1.1 Twin State | Nothing (start here) | Everything: 1.2, 1.3, 2.1–2.6, 3.1, 3.2 |
| 1.2 Scenarios | 1.1 Twin State | 1.3 Cases, 2.6 Weather |
| 1.3 Cases | 1.1 Twin State, 1.2 Scenarios | 3.2 Evaluation, 3.3 Integration |
| 1.4 RAG | Nothing (parallel with 1.1) | 2.2 Operations Agent, 2.4 Governance Agent |
| 2.1 Graph | 1.1 Twin State | 2.2–2.5 All agents |
| 2.2 Operations Agent | 2.1 Graph, 1.4 RAG | 2.4 Governance Agent |
| 2.3 Cost Agent | 2.1 Graph, 1.1 Twin State | 2.4 Governance Agent |
| 2.4 Governance Agent | 2.2 Operations, 2.3 Cost, 1.4 RAG | 2.5 Supervisor, 3.1 UI |
| 2.5 Supervisor | 2.4 Governance Agent | 3.1 UI, 3.3 Integration |
| 2.6 Weather | 1.2 Scenarios | 3.3 Integration (non-blocking) |
| 3.1 UI | 2.4 Governance, 2.5 Supervisor | 3.3 Integration, 4.1 Demo |
| 3.2 Evaluation | 1.3 Cases, 1.1 Twin State | 3.3 Integration |
| 3.3 Integration | All above | 4.1 Demo |

Risk Register

| Risk | Likelihood | Impact | Trigger Signal | Mitigation |
| --- | --- | --- | --- | --- |
| LLM structured output fails | Medium | High | Agent returns malformed JSON in >20% of calls | Add output validation + retry logic; use function calling mode |
| Scope creep into strategic layer | High | High | Spending time on simulation engine instead of operational flow | Strategic layer = scenario selector only. Stop. |
| Cost function inconsistency | Medium | Medium | Evaluation metrics don’t match hand-calculated expectations | Build cost tests in Week 1; verify before building agents |
| Weather API rate limit | Low | Low | API returns 429 errors | Fallback mechanism handles this automatically |
| Demo crashes during presentation | Medium | Critical | Streamlit error during live demo | Pre-cached case runs + backup notebook demo |
| Time overrun | High | High | Week 2 not complete by end of Week 2 | Cut: skip Verify mode, reduce to 8 cases, simplify UI |

Emergency Scope Cuts (if behind schedule)

If you reach the end of Week 2 and the pipeline is not running end-to-end, execute these cuts in order:

- Drop “Verify” mode from Supervisor: only Approve and Override. Saves ~2 hours of UI and logic work.

- Reduce cases from 15 to 8 (3 easy, 3 medium, 2 hard). Saves ~3 hours of case design and testing.

- Simplify Streamlit UI: drop expandable sections, show all Governance output as plain text. Saves ~4 hours.

- Drop Weather API entirely: use only synthetic disruption data. Saves ~2 hours.

- If truly desperate: drop Streamlit entirely, demo in Jupyter notebook with markdown-formatted output. Last resort.

Remember: A working demo with 8 cases and a simple UI is infinitely better than an ambitious system that crashes during the presentation. Protect the critical path. Ship what works.